## Import Project Template
| Project name: | TEST Development of Daladala terminal, Market and Commercial building at Chuini
field:sectors | Sector/s: | Urban Municipal
field:regions | Region: | Urban West - West A
field:stage | Phase: | Preparation
field:sponsor | Implementing Authority: | West ‘A’ Municipal Council
field:project_value_usd | Project value (USD): | 7.6 |  | (It will be formatted as 7.6)
field:project_value_second | Project value (TZS): | 18,238 |  | (It will be formatted as 18.238)
field:project_need | Project need: | Located in a village, 12 Kms North of the capital in Unguja, Chuini is a critical junction which attracts lots of public utility vehicle (PUV) traffic (from Bububu/town, North A and West A) but lacks a bus terminal and formal market with adequate facilities to manage high volume of buses/ daladalas and accommodate buying and selling of goods in the locality. WAMC intends to develop a bus terminal facility with adequate capacity to handle the increasing traffic of public transport. Without bus terminal facility, the PUV at Chuini are operating along the main road reducing the effective road carriageway. During the rush/peak hours, situation becomes worse with more vehicles on the road, which is unsafe for commuters. This has prompted the West A Municipal Council to propose for a bus/ daladala terminal with a commercial complex.
field:description_asset | Description of asset: | The various facilities proposed within the bus/daladala terminal include 58 boarding bays , 29 alighting bays, 174 idle/staging bays, vehicle and pedestrian circulation areas, passenger concourse, terminal schedule (information display) with public address system, scheduling system, driver retiring room, information kiosk/ enquiry counter and complaint desks, security system, service centre for minor repairs of buses and other vehicles, firefighting system and power backup, commercial spaces, market facility and other support facilities.
field:description_services | Description of services: | Provision of departures for daladalas/buses, pedestrian entry/exit points of the bus terminal building, pedestrian circulation/movement, seating spaces for passengers in waiting areas, departure, alighting and idle/staging bays, parking bays for private cars and two wheelers, collection of terminal fee revenue, schedule/information display system, closed circuit television system, rest rooms / toilets, information kiosks, complaint desks, public address system, drinking water faucets/taps, waste management as well as pest control and fire safety
field:reasons_ppp | Rationale for selection of PPP model: | Implementing this project under PPP modality will provide avenue for the private sector player to design, develop and operate the project on a long term basis, giving full freedom and flexibility to create a robust revenue stream for the project, take the requisite measures to develop the project into a hub within vicinity. Under the PPP model, the project will also develop skills, expertise and business acumen of the PSP. The proposed Project may be proceeded with the typical Design, Finance, Build, Operate, Maintenance and Transfer (DFBOM) with core project responsibility lying with Concessionaire and the IA mainly managing & monitoring the concessions as per the terms and conditions contained in the PPP Agreement. The role of the IA will be restricted to the management of the Concession throughout the Concession Period and see to it that the “mandatory development obligations” carved out for the Concessionaire in the PPP Agreement shall be performed by the Concessionaire during the term of the PPP Agreement. However, the Project being a complex in nature, the IA need to assist the Concessionaire in marketing the facilities to the general public to attract/ and further increase the influx of users, by endorsing the same. The monitoring will be through an Independent Expert who shall perform its functions based on the terms laid out in the PPP Agreement.
field:stakeholder_consultation | Community enagement: | Survey was launched during the Feasibility Study enabled the council to understand the current situation from the target beneficiaries’ viewpoint. Interview was conducted with 42 drivers interviewed, 42 passengers, and 84 traders. Thus, in the survey conducted, 85% of the respondents stated that if a terminal facility with commercial spaces for rent will be established within the vicinity, they will be supportive of it. Some of the project benefits identified included: (1) comfort and safety, (2) better security in the area, (3) better/cleaner environment may impact on health and eliminate hazards, and (4) potential to attract tourists to use public transport or purchase items from the commercial complex. These perceived benefits influence the high acceptability of the project from the viewpoint of the target beneficiaries, indicating that the proposed project will bring about positive impact on the overall well-being of the public.
field:project_summary_document | Project Concept Note:
section:contract_milestones | Project Milestones
columns:name,relation[milestones_types;name;milestone_type_id],relation[milestones_categories;name;milestone_category_id],date,description | Milestone | Type | Category | Timeline | Responsible
| Initial screening of PPP Opportunity | Estimated milestone | Identification | 2016-06-21 | Public Authority
| Project Manager Appointed | Actual milestone | Identification | 2016-06-21 | Public Authority
| Project Management Team Consituted | Estimated milestone | Identification | 2016-06-21 | Public Authority
| Project Concept Note screened | Estimated milestone | Identification | 2016-06-21 | Public Authority
| Project proposal enters list of published projects pipeline | Estimated milestone | Identification | 2016-05-24 | Public Authority
| Pre - Feasibility Study Report Approved | Actual milestone | Preparation | 2016-06-21 | PPP Department
| Community Engagement Report | Actual milestone | Preparation | 2016-06-21 | Public Authority
| Environmental and Social Due Diligence Report | Actual milestone | Preparation | 2016-06-21 | Public Authority
| Advisors to conduct Feasibility Study appointed | Actual milestone | Preparation | 2016-06-21 | Public Authority
| Feasibility Study Approved | Actual milestone | Preparation | 2016-05-24 | Public Authority
| Appoint Transaction Advisors | Actual milestone | Preparation | 2016-06-21 | Public Authority
| Conduct Market Sounding | Actual milestone | Preparation | 2016-06-21 | Public Authority
| Approve and release RFQ | Estimated milestone | Tendering | 2016-06-21 | PPP Department
| Data Room Established | Estimated milestone | Tendering | 2016-06-21 | Public Authority
| Bidders Conference | Estimated milestone | Tendering | 2016-05-24 | Public Authority
| Evaluation of RfQs submitted by the prospective bidders | Estimated milestone | Tendering | 2016-06-21 | PPP Department
| Declaration of pre-qualified bidders as under Regulations 33 of the PPP Regulations | Estimated milestone | Tendering | 2016-06-21 | Public Authority
| Finalization of RFP, Draft PPP Agreement and its Schedules (Bid Documents) | Estimated milestone | Tendering | 2016-06-21 | Public Authority
| Issuance of bid documents to the pre-qualified bidders | Actual milestone | Tendering | 2016-06-21 | Public Authority
| Pre-bid conference | Actual milestone | Tendering | 2016-05-24 | Public Authority
| Submission of queries by the Pre-qualified bidders based on Pre-bid conference | Actual milestone | Tendering | 2016-06-21 | Public Authority
| Sharing of the minutes of the Pre- Bid Conference by the IA with the Pre-Qualified Bidders who attended the pre-bid conference and response to queries raised by them and any corrigenda or addenda to be issued | Actual milestone | Tendering | 2016-06-21 | PPP Department
| Competitive dialogue Process | Actual milestone | Tendering | 2016-06-21 | Public Authority
| Issuance of Final Bid Documents | Actual milestone | Tendering | 2016-06-21 | Public Authority
| Constitution of Proposal Evaluation Team | Actual milestone | Tendering | 2016-05-24 | Public Authority
| Submission of proposals by the Pre-Qualified Bidders | Actual milestone | Tendering | 2016-06-21 | Public Authority
| Evaluation of proposals and declaration of the Preferred Bidder | Actual milestone | Tendering | 2016-06-21 | Public Authority
| Issuance of letter of Acceptance (LOA) to the Preferred Bidder and communication of the same to the other Pre-Qualified Bidders who have submitted the bids. | Estimated milestone | Award | 2016-06-21 | PPP Department
| Confirmation in writing their acknowledgement thereof of the receipt of the LOA by the winning successful bidder | Estimated milestone | Award | 2016-06-21 | Public Authority
| Establishment of project company | Estimated milestone | Award | 2016-05-24 | Public Authority
| Signing of a PPP Agreement with the SPV incorporated by winning/ successful bidder | Estimated milestone | Award | 2016-06-21 | Public Authority
| Financial Closure of the project | Estimated milestone | Award | 2016-06-21 | Public Authority
| Publication of White Book | Estimated milestone | Award | 2016-06-21 | Public Authority
| Completion of the conditions Precedent by IA and the SPV/Project Company | Actual milestone | Implementation | 2016-06-21 | Public Authority
| Financial Close | Actual milestone | Implementation | 2016-05-24 | Public Authority
| Construction Phase | Actual milestone | Implementation | 2016-06-21 | Public Authority
| Operation Phase | Actual milestone | Implementation | 2016-06-21 | PPP Department
| Handback of the project | Actual milestone | Handover | 2016-06-21 | Public Authority
section:pd_procurement | Procurement Documents
columns:name,description | Name | Description
section:parties | Parties
Sponsoring Agency
Private Agencies
section:pd_document | Contract Information - Redacted PPP agreement
columns:name,description | Name | Description
Document 1
Document 2
Document 3
section:pd_financial | Contract Information - Financial Structure
columns:name,description | Name | Description
Equity-debt ratio
Share capital
Shareholders
Other information
section:pd_risks | Contract Information - Risks
columns:name,description,relation[pd_risks_allocation;name;risk_allocation_id],mitigation | Name | Description | Allocation | Mitigation
section:pd_government_support | Contract Information - Government Support
columns:name,description | Name | Description
Guarantees
Grants
Service payments
Land Leases, Asset Transfers
Other support
Revenue share
section:pd_tariffs | Contract Information - Tariffs
columns:name,description | Name | Description
| Tariff 1 | Tariff description
| Tariff 2 | Tariff description
| Tariff 3 | Tariff description
| Tariff 4 | Tariff description
| Tariff 5 | Tariff description
| Tariff 6 | Test
section:pd_contract_termination | Contract Information - Termination Provisions
columns:party_type,name,description,termination_payment | Party | Name | Description | Termination Payment
| Authority | Event | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis. | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis.
| Authority | Event | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis. | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis.
| Authority | Event | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis. | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis.
| Authority | Event | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis. | Ad eum alia porro, nec ei aliquip laoreet. Sed no consul impetus. An esse iuvaret qui. Iudico phaedrum intellegat nec ut, libris dolorum an eam, sea at habeo admodum maiestatis.
section:pd_renegotiations | Contract Information - Renegotiations
columns:name,description | Name | Description
| Rationale for variation | Soluta numquam pro ei, mel id civibus iudicabit iracundia. Eam affert percipit ea. Alterum noluisse his ea. Vis in erant viris. Ei sit iusto tation repudiandae, quas altera referrentur est at.
| Change in roles and responsibilities of the parties | Soluta numquam pro ei, mel id civibus iudicabit iracundia. Eam affert percipit ea. Alterum noluisse his ea. Vis in erant viris. Ei sit iusto tation repudiandae, quas altera referrentur est at.
| Change in original risk allocation | Soluta numquam pro ei, mel id civibus iudicabit iracundia. Eam affert percipit ea. Alterum noluisse his ea. Vis in erant viris. Ei sit iusto tation repudiandae, quas altera referrentur est at.
| Change in original fiscal commitments or contingent liabilities of government | Soluta numquam pro ei, mel id civibus iudicabit iracundia. Eam affert percipit ea. Alterum noluisse his ea. Vis in erant viris. Ei sit iusto tation repudiandae, quas altera referrentur est at.
| Change in tariffs of service levels | Soluta numquam pro ei, mel id civibus iudicabit iracundia. Eam affert percipit ea. Alterum noluisse his ea. Vis in erant viris. Ei sit iusto tation repudiandae, quas altera referrentur est at.
| Date of variation | Soluta numquam pro ei, mel id civibus iudicabit iracundia. Eam affert percipit ea. Alterum noluisse his ea. Vis in erant viris. Ei sit iusto tation repudiandae, quas altera referrentur est at.
section:kpi | Performance Information - Key Performance Indicators
| Year | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019 | 2019 | 2020 | 2019
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement
| Water loses(m³) | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 50 | 5 | 50
| Energy loses(m³) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
section:pi_performance_failures | Performance Information - Performance Failures
columns:title,relation[pi_performance_failures_category;name;category_failure_id],number_events,penalty_contract,penalty_imposed,penalty_paid | Title | Category of failure | Number of events | Penalty or abatement provided in contract | Penalty or abatement imposed | Penalty paid or abatement effected: Yes/No
| Performance failure 1 | Financial objectives | 1 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | Yes
| Performance failure 2 | Transparency in accounting and in operations | 2 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | No
| Performance failure 3 | Transparency in accounting and in operations | 3 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | Yes
| Performance failure 4 | Transparency in accounting and in operations | 1 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea. | No
section:pi_performance_assessment | Performance Information - Performance Assesments
columns:name,description | Name | Description
| Audit reports | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Audited Financial Statements | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Private party reports | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Independent Expert reports | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
section:pd_announcements | Announcements
columns:name,description | Name | Description
| Announcement 1 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Announcement 2 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Announcement 3 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Announcement 4 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Announcement 5 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Announcement 6 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.
| Announcement 7 | Lorem ipsum dolor sit amet, ne eam dicat nostrum. Ad zril principes vim, nec etiam alienum in, eos molestie facilisis interesset at. Magna iracundia inciderint cum ut, at vis suscipit nominati efficiendi. Id intellegat inciderint usu, ea unum dicta scripta has, aeque dissentiet per id. Vel no feugiat graecis. Est purto dissentias ea.